{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["3.1 表-08 分部分项工程和单价措施项目清单与计价表","3.2 表-11 总价措施项目清单与计价表","3.3 表-12 其他项目清单与计价汇总表","3.4 表-13 规费、税金项目计价表","3.5 表-21 承包人材料设备（适用于造价信息差额调整法）"],"not_rendered":{"external_links":1,"defined_names":5},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"3.1 表-08 分部分项工程和单价措施项目清单与计价表","index":0,"n_rows":155,"n_cols":12,"rows_kept":155,"merged":[[0,0,0,11],[1,0,1,3],[1,4,1,9],[1,10,1,11],[2,0,4,0],[2,1,4,1],[2,2,4,2],[2,3,4,4],[2,5,4,5],[2,6,4,7],[2,8,2,11],[3,8,4,8],[3,9,4,10],[5,3,5,4],[5,6,5,7],[5,9,5,10],[6,3,6,4],[6,6,6,7],[6,9,6,10],[7,0,8,0],[7,1,8,1],[7,2,8,2],[7,3,8,4],[7,5,8,5],[7,6,8,7],[7,8,8,8],[7,9,8,10],[7,11,8,11],[9,0,10,0],[9,1,10,1],[9,2,10,2],[9,3,10,4],[9,5,10,5],[9,6,10,7],[9,8,10,8],[9,9,10,10],[9,11,10,11],[11,0,12,0],[11,1,12,1],[11,2,12,2],[11,3,12,4],[11,5,12,5],[11,6,12,7],[11,8,12,8],[11,9,12,10],[11,11,12,11],[13,3,13,4],[13,6,13,7],[13,9,13,10],[14,3,14,4],[14,6,14,7],[14,9,14,10],[15,3,15,4],[15,6,15,7],[15,9,15,10],[16,3,16,4],[16,6,16,7],[16,9,16,10],[17,3,17,4],[17,6,17,7],[17,9,17,10],[18,3,18,4],[18,6,18,7],[18,9,18,10],[19,3,19,4],[19,6,19,7],[19,9,19,10],[20,3,20,4],[20,6,20,7],[20,9,20,10],[21,3,21,4],[21,6,21,7],[21,9,21,10],[22,3,22,4],[22,6,22,7],[22,9,22,10],[23,0,23,8],[23,9,23,10],[25,7,25,11],[26,0,26,11],[27,0,27,3],[27,4,27,9],[27,10,27,11],[28,0,30,0],[28,1,30,1],[28,2,30,2],[28,3,30,4],[28,5,30,5],[28,6,30,7],[28,8,28,11],[29,8,30,8],[29,9,30,10],[31,0,33,0],[31,1,33,1],[31,2,33,2],[31,3,33,4],[31,5,33,5],[31,6,33,7],[31,8,33,8],[31,9,33,10],[31,11,33,11],[34,0,36,0],[34,1,36,1],[34,2,36,2],[34,3,36,4],[34,5,36,5],[34,6,36,7],[34,8,36,8],[34,9,36,10],[34,11,36,11],[37,0,38,0],[37,1,38,1],[37,2,38,2],[37,3,38,4],[37,5,38,5],[37,6,38,7],[37,8,38,8],[37,9,38,10],[37,11,38,11],[39,0,40,0],[39,1,40,1],[39,2,40,2],[39,3,40,4],[39,5,40,5],[39,6,40,7],[39,8,40,8],[39,9,40,10],[39,11,40,11],[41,0,42,0],[41,1,42,1],[41,2,42,2],[41,3,42,4],[41,5,42,5],[41,6,42,7],[41,8,42,8],[41,9,42,10],[41,11,42,11],[43,3,43,4],[43,6,43,7],[43,9,43,10],[44,3,44,4],[44,6,44,7],[44,9,44,10],[45,3,45,4],[45,6,45,7],[45,9,45,10],[46,0,46,8],[46,9,46,10],[48,7,48,11],[49,0,49,11],[50,0,50,3],[50,4,50,9],[50,10,50,11],[51,0,53,0],[51,1,53,1],[51,2,53,2],[51,3,53,4],[51,5,53,5],[51,6,53,7],[51,8,51,11],[52,8,53,8],[52,9,53,10],[54,0,55,0],[54,1,55,1],[54,2,55,2],[54,3,55,4],[54,5,55,5],[54,6,55,7],[54,8,55,8],[54,9,55,10],[54,11,55,11],[56,3,56,4],[56,6,56,7],[56,9,56,10],[57,3,57,4],[57,6,57,7],[57,9,57,10],[58,0,59,0],[58,1,59,1],[58,2,59,2],[58,3,59,4],[58,5,59,5],[58,6,59,7],[58,8,59,8],[58,9,59,10],[58,11,59,11],[60,0,61,0],[60,1,61,1],[60,2,61,2],[60,3,61,4],[60,5,61,5],[60,6,61,7],[60,8,61,8],[60,9,61,10],[60,11,61,11],[62,3,62,4],[62,6,62,7],[62,9,62,10],[63,0,65,0],[63,1,65,1],[63,2,65,2],[63,3,65,4],[63,5,65,5],[63,6,65,7],[63,8,65,8],[63,9,65,10],[63,11,65,11],[66,3,66,4],[66,6,66,7],[66,9,66,10],[67,3,67,4],[67,6,67,7],[67,9,67,10],[68,0,68,8],[68,9,68,10],[70,7,70,11],[71,0,71,11],[72,0,72,3],[72,4,72,9],[72,10,72,11],[73,0,75,0],[73,1,75,1],[73,2,75,2],[73,3,75,4],[73,5,75,5],[73,6,75,7],[73,8,73,11],[74,8,75,8],[74,9,75,10],[76,0,78,0],[76,1,78,1],[76,2,78,2],[76,3,78,4],[76,5,78,5],[76,6,78,7],[76,8,78,8],[76,9,78,10],[76,11,78,11],[79,0,81,0],[79,1,81,1],[79,2,81,2],[79,3,81,4],[79,5,81,5],[79,6,81,7],[79,8,81,8],[79,9,81,10],[79,11,81,11],[82,0,83,0],[82,1,83,1],[82,2,83,2],[82,3,83,4],[82,5,83,5],[82,6,83,7],[82,8,83,8],[82,9,83,10],[82,11,83,11],[84,0,85,0],[84,1,85,1],[84,2,85,2],[84,3,85,4],[84,5,85,5],[84,6,85,7],[84,8,85,8],[84,9,85,10],[84,11,85,11],[86,3,86,4],[86,6,86,7],[86,9,86,10],[87,3,87,4],[87,6,87,7],[87,9,87,10],[88,3,88,4],[88,6,88,7],[88,9,88,10],[89,3,89,4],[89,6,89,7],[89,9,89,10],[90,0,90,8],[90,9,90,10],[92,7,92,11],[93,0,93,11],[94,0,94,3],[94,4,94,9],[94,10,94,11],[95,0,97,0],[95,1,97,1],[95,2,97,2],[95,3,97,4],[95,5,97,5],[95,6,97,7],[95,8,95,11],[96,8,97,8],[96,9,97,10],[98,0,99,0],[98,1,99,1],[98,2,99,2],[98,3,99,4],[98,5,99,5],[98,6,99,7],[98,8,99,8],[98,9,99,10],[98,11,99,11],[100,0,101,0],[100,1,101,1],[100,2,101,2],[100,3,101,4],[100,5,101,5],[100,6,101,7],[100,8,101,8],[100,9,101,10],[100,11,101,11],[102,0,103,0],[102,1,103,1],[102,2,103,2],[102,3,103,4],[102,5,103,5],[102,6,103,7],[102,8,103,8],[102,9,103,10],[102,11,103,11],[104,0,105,0],[104,1,105,1],[104,2,105,2],[104,3,105,4],[104,5,105,5],[104,6,105,7],[104,8,105,8],[104,9,105,10],[104,11,105,11],[106,0,107,0],[106,1,107,1],[106,2,107,2],[106,3,107,4],[106,5,107,5],[106,6,107,7],[106,8,107,8],[106,9,107,10],[106,11,107,11],[108,3,108,4],[108,6,108,7],[108,9,108,10],[109,3,109,4],[109,6,109,7],[109,9,109,10],[110,0,110,8],[110,9,110,10],[112,7,112,11],[113,0,113,11],[114,0,114,3],[114,4,114,9],[114,10,114,11],[115,0,117,0],[115,1,117,1],[115,2,117,2],[115,3,117,4],[115,5,117,5],[115,6,117,7],[115,8,115,11],[116,8,117,8],[116,9,117,10],[118,0,119,0],[118,1,119,1],[118,2,119,2],[118,3,119,4],[118,5,119,5],[118,6,119,7],[118,8,119,8],[118,9,119,10],[118,11,119,11],[120,2,120,4],[120,6,120,7],[120,9,120,10],[121,3,121,4],[121,6,121,7],[121,9,121,10],[122,3,122,4],[122,6,122,7],[122,9,122,10],[123,3,123,4],[123,6,123,7],[123,9,123,10],[124,3,124,4],[124,6,124,7],[124,9,124,10],[125,3,125,4],[125,6,125,7],[125,9,125,10],[126,3,126,4],[126,6,126,7],[126,9,126,10],[127,3,127,4],[127,6,127,7],[127,9,127,10],[128,3,128,4],[128,6,128,7],[128,9,128,10],[129,3,129,4],[129,6,129,7],[129,9,129,10],[130,3,130,4],[130,6,130,7],[130,9,130,10],[131,3,131,4],[131,6,131,7],[131,9,131,10],[132,3,132,4],[132,6,132,7],[132,9,132,10],[133,3,133,4],[133,6,133,7],[133,9,133,10],[134,3,134,4],[134,6,134,7],[134,9,134,10],[135,3,135,4],[135,6,135,7],[135,9,135,10],[136,3,136,4],[136,6,136,7],[136,9,136,10],[137,3,137,4],[137,6,137,7],[137,9,137,10],[138,3,138,4],[138,6,138,7],[138,9,138,10],[139,3,139,4],[139,6,139,7],[139,9,139,10],[140,3,140,4],[140,6,140,7],[140,9,140,10],[141,3,141,4],[141,6,141,7],[141,9,141,10],[142,3,142,4],[142,6,142,7],[142,9,142,10],[143,3,143,4],[143,6,143,7],[143,9,143,10],[144,3,144,4],[144,6,144,7],[144,9,144,10],[145,3,145,4],[145,6,145,7],[145,9,145,10],[146,3,146,4],[146,6,146,7],[146,9,146,10],[147,3,147,4],[147,6,147,7],[147,9,147,10],[148,3,148,4],[148,6,148,7],[148,9,148,10],[149,3,149,4],[149,6,149,7],[149,9,149,10],[150,3,150,4],[150,6,150,7],[150,9,150,10],[151,0,151,8],[151,9,151,10],[152,0,152,8],[152,9,152,10],[154,7,154,11]],"flags":["formulas_cached_only"]}
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第1页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["1","011606003001","天棚面龙骨及饰面拆除","1、拆除部位：卫生间铝扣板吊顶\n2、拆除出垃圾外运出校，投标单位自主报价，结算时不再调整",null,"m2","65.87"]
["2","011609002001","隔断隔墙拆除","1、拆除部位：卫生间蹲便器隔断\n2、拆除出垃圾外运出校，投标单位自主报价，结算时不再调整",null,"间","16"]
["3","011605001001","平面块料拆除","1、拆除部位：地面地砖\n2、拆除至结构层后水泥砂浆找平\n3、拆除后垃圾外运出校园，投标单位自主报价，结算时不再调整",null,"m2","65.88"]
[]
["4","011605002001","立面块料拆除","1、拆除部位：墙面墙砖\n2、拆除至结构层后水泥砂浆找平\n3、拆除后垃圾外运出校园，投标单位自主报价，结算时不再调整",null,"m2","250.2"]
[]
["5","011614001001","其他管线设施拆除","1、拆除部位：卫生间\n2、房间内所有给排水管道、附件及卫生洁具等零星拆除项目\n3、拆除出的垃圾外运出校，投标单位实地勘察自主报价，结算时不再调整",null,"间","4"]
[]
["6","010904002001","楼（地）面涂膜防水","1、部位：卫生间\n2、2.0mm厚聚氨酯防水层\n3、翻边高度300mm",null,"m2","88.39"]
{"$rows_empty":9}
["本页小计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第2页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["7","011102003001","块料楼地面","1、部位：卫生间地砖\n2、20厚1:3水泥砂浆找平\n3、素水泥浆一道，内掺801胶\n4、20厚1:3干硬性水泥砂浆结合层\n5、8~10厚300*300防滑地砖贴面，干水泥擦缝\n6、面砖厂家品牌：冠军、强辉、新中源等同等品质品牌",null,"m2","65.87"]
[]
[]
["8","011204003001","块料墙面","1、部位：卫生间墙砖\n2、12厚1：3水泥砂浆找平层\n3、6厚1:0.1:2.5混合砂浆粘接层\n4、901胶素水泥浆一道\n5、300*600内墙面砖贴面\n6、面砖厂家品牌：冠军、强辉、新中源等同等品质品牌",null,"m2","250.2"]
[]
[]
["9","011302001001","吊顶天棚","1、部位：卫生间吊顶\n2、面层规格：600*600*0.8铝扣板\n3、配套龙骨及边角\n4、∅8全丝吊杆、50轻钢龙骨",null,"m2","65.88"]
[]
["10","011505001001","洗漱台","1、部位：洗脸盆台面\n2、材料品种、规格、颜色：卡特灰大理石面层\n3、支架、配件品种、规格：不锈钢角钢支架",null,"m2","3.51"]
[]
["11","011505010001","镜面玻璃","1、镜面玻璃品种、规格：6mm厚镀银镜面玻璃\n2、框材质、断面尺寸：50mm宽实木框\n3、基层材料种类：18mm厚细木工板",null,"m2","3.51"]
[]
[]
[]
[]
["本页小计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第3页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["12","011210005001","成品隔断","1、卫生间成品高隔断\n2、隔断材料品种、规格、颜色：12mm仿木纹抗倍特板\n3、配件品种、规格。：太空铝",null,"间","16"]
[]
["13","030412005001","荧光灯","1、部位：卫生间照明灯具\n2、600*600LED灯盘、主材甲供\n3、安装方式：嵌入式",null,"套","10"]
["14","030404034001","照明开关","1、名称：单联开关\n2、规格：220V/10A\n3、安装方式：暗装\n4、厂家品牌：正泰、德力西、罗格朗或同等知名品牌",null,"个","4"]
["15","030411001001","配管","1、名称：刚性阻燃管\n2、规格：PC20\n3、配置形式：砖混暗配\n4、厂家品牌：联塑、中财、伟星同等知名品牌",null,"m","31.2"]
[]
["16","030411004001","配线","1、名称：管内穿线\n2、配线形式：照明线路\n3、规格：BV-2.5mm2\n4、厂家品牌：铜山、远东、宝胜或同等知名品牌",null,"m","93.6"]
[]
["17","030411006001","接线盒","1、名称：PVC接线盒\n2、规格：H86\n3、安装形式：安装",null,"个","14"]
["18","031001006002","塑料管","1、安装部位：室内\n2、介质：冷水\n3、材质、规格：PP-R冷水管dn25X2.3\n4、连接形式：热熔连接\n5、含过墙楼板开孔及封堵\n6、工作压力1.5倍水压试验，消毒清洗\n7、厂家品牌：联塑、中财、金牛同等知名品牌",null,"m","7.8"]
[]
[]
[]
[]
["本页小计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第4页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["19","031001006003","塑料管","1、安装部位：室内\n2、介质：冷水\n3、材质、规格：PP-R冷水管dn32X3\n4、连接形式：热熔连接\n5、含过墙楼板开孔及封堵\n6、工作压力1.5倍水压试验，消毒清洗\n7、厂家品牌：联塑、中财、金牛同等知名品牌",null,"m","22.6"]
[]
[]
["20","031001006004","塑料管","1、安装部位：室内\n2、介质：冷水\n3、材质、规格：PP-R冷水管dn63X5.8\n4、连接形式：热熔连接\n5、含过墙楼板开孔及封堵\n6、工作压力1.5倍水压试验，消毒清洗\n7、厂家品牌：联塑、中财、金牛同等知名品牌",null,"m","6.4"]
[]
[]
["21","031001006005","塑料管","1、安装部位：室内\n2、介质：污水\n3、材质、规格：PVC-U排水管dn50X2\n4、连接形式：零件粘接\n5、含过墙楼板开孔及封堵\n6、厂家品牌：联塑、中财、伟星或同等知名品牌",null,"m","10.2"]
[]
["22","031001006006","塑料管","1、安装部位：室内\n2、介质：污水\n3、材质、规格：PVC-U排水管dn110X3.2\n4、连接形式：零件粘接\n5、含过墙楼板开孔及封堵\n6、厂家品牌：联塑、中财、伟星或同等知名品牌",null,"m","40.8"]
[]
[]
[]
[]
[]
["本页小计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第5页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["23","031003001003","PPR阀门","1、类型：PPR截止阀\n2、规格、压力等级：DN32\n3、连接形式：热熔连接\n4、厂家品牌：联塑、中财、金牛或同等知名品牌",null,"个","2"]
[]
["24","031004003001","洗脸盆","1、材质：白瓷\n2、规格、类型：台上盆\n3、组装形式：冷水\n4、附件名称、数量：角阀1个、不锈钢软管1根，不锈钢落水口1套，配套水龙头1个\n5、厂家品牌：美标、箭牌、东鹏或同等知名品牌",null,"组","4"]
[]
["25","031004004001","洗涤盆","1、材质：白瓷\n2、规格、类型：拖布盆\n3、组装形式：单嘴\n4、附件名称、数量：不锈钢下水口1套，水龙头1个\n5、厂家品牌：美标、箭牌、东鹏或同等知名品牌",null,"组","4"]
[]
["26","031004006001","大便器","1、材质：白瓷\n2、规格、类型：大号蹲便器\n3、组装形式：脚踏延时阀冲洗\n4、附件名称、数量：手按延时阀套件1套\n5、厂家品牌：美标、箭牌、东鹏等知名品牌",null,"组","16"]
[]
["27","031004007001","小便器","1、材质：白瓷\n2、规格、类型：挂式小便器\n3、组装形式：感应式冲洗暗装\n4、附件名称、数量：感应式冲洗器1套\n5、厂家品牌：美标、箭牌、东鹏等知名品牌",null,"组","6"]
[]
[]
[]
["本页小计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]
["分部分项工程和单价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":5},"第6页 共6页"]
["序号","项目编码","项目名称","项目特征描述",null,"计量\n单位","工程量",null,"金额（元）"]
[{"$nulls":8},"综合单价","合价",null,"其中"]
[{"$nulls":11},"暂估价"]
["28","031004014001","给、排水附（配）件","1、材质：不锈钢地漏\n2、型号、规格：DN50\n3、厂家品牌：美标、箭牌、东鹏等知名品牌",null,"个","6"]
[]
[null,null,"分部分项合计",{"$nulls":3},""]
{"$rows_empty":30}
["本页小计"]
["合    计"]
[]
[{"$nulls":7},"【新点2013清单造价江苏版 V10.3.2】"]

{"sheet":"3.2 表-11 总价措施项目清单与计价表","index":1,"n_rows":53,"n_cols":13,"rows_kept":53,"merged":[[0,0,0,13],[1,0,1,5],[1,6,1,10],[1,11,1,13],[2,2,2,3],[2,5,2,6],[2,7,2,8],[2,10,2,11],[2,12,2,13],[3,2,3,3],[3,5,3,6],[3,7,3,8],[3,10,3,11],[3,12,3,13],[4,2,4,3],[4,5,4,6],[4,7,4,8],[4,10,4,11],[4,12,4,13],[5,2,5,3],[5,5,5,6],[5,7,5,8],[5,10,5,11],[5,12,5,13],[6,2,6,3],[6,5,6,6],[6,7,6,8],[6,10,6,11],[6,12,6,13],[7,2,7,3],[7,5,7,6],[7,7,7,8],[7,10,7,11],[7,12,7,13],[8,2,8,3],[8,5,8,6],[8,7,8,8],[8,10,8,11],[8,12,8,13],[9,2,9,3],[9,5,9,6],[9,7,9,8],[9,10,9,11],[9,12,9,13],[10,2,10,3],[10,5,10,6],[10,7,10,8],[10,10,10,11],[10,12,10,13],[11,2,11,3],[11,5,11,6],[11,7,11,8],[11,10,11,11],[11,12,11,13],[12,2,12,3],[12,5,12,6],[12,7,12,8],[12,10,12,11],[12,12,12,13],[13,2,13,3],[13,5,13,6],[13,7,13,8],[13,10,13,11],[13,12,13,13],[14,2,14,3],[14,5,14,6],[14,7,14,8],[14,10,14,11],[14,12,14,13],[15,2,15,3],[15,5,15,6],[15,7,15,8],[15,10,15,11],[15,12,15,13],[16,0,16,13],[17,8,17,13],[18,0,18,2],[18,8,18,12],[19,0,19,13],[20,0,20,5],[20,6,20,10],[20,11,20,13],[21,2,21,3],[21,5,21,6],[21,7,21,8],[21,10,21,11],[21,12,21,13],[22,2,22,3],[22,5,22,6],[22,7,22,8],[22,10,22,11],[22,12,22,13],[23,2,23,3],[23,5,23,6],[23,7,23,8],[23,10,23,11],[23,12,23,13],[24,2,24,3],[24,5,24,6],[24,7,24,8],[24,10,24,11],[24,12,24,13],[25,2,25,3],[25,5,25,6],[25,7,25,8],[25,10,25,11],[25,12,25,13],[26,2,26,3],[26,5,26,6],[26,7,26,8],[26,10,26,11],[26,12,26,13],[27,2,27,3],[27,5,27,6],[27,7,27,8],[27,10,27,11],[27,12,27,13],[28,2,28,3],[28,5,28,6],[28,7,28,8],[28,10,28,11],[28,12,28,13],[29,2,29,3],[29,5,29,6],[29,7,29,8],[29,10,29,11],[29,12,29,13],[30,2,30,3],[30,5,30,6],[30,7,30,8],[30,10,30,11],[30,12,30,13],[31,2,31,3],[31,5,31,6],[31,7,31,8],[31,10,31,11],[31,12,31,13],[32,2,32,3],[32,5,32,6],[32,7,32,8],[32,10,32,11],[32,12,32,13],[33,2,33,3],[33,5,33,6],[33,7,33,8],[33,10,33,11],[33,12,33,13],[34,2,34,3],[34,5,34,6],[34,7,34,8],[34,10,34,11],[34,12,34,13],[35,2,35,3],[35,5,35,6],[35,7,35,8],[35,10,35,11],[35,12,35,13],[36,2,36,3],[36,5,36,6],[36,7,36,8],[36,10,36,11],[36,12,36,13],[37,2,37,3],[37,5,37,6],[37,7,37,8],[37,10,37,11],[37,12,37,13],[38,2,38,3],[38,5,38,6],[38,7,38,8],[38,10,38,11],[38,12,38,13],[39,2,39,3],[39,5,39,6],[39,7,39,8],[39,10,39,11],[39,12,39,13],[40,2,40,3],[40,5,40,6],[40,7,40,8],[40,10,40,11],[40,12,40,13],[41,2,41,3],[41,5,41,6],[41,7,41,8],[41,10,41,11],[41,12,41,13],[42,2,42,3],[42,5,42,6],[42,7,42,8],[42,10,42,11],[42,12,42,13],[43,2,43,3],[43,5,43,6],[43,7,43,8],[43,10,43,11],[43,12,43,13],[44,2,44,3],[44,5,44,6],[44,7,44,8],[44,10,44,11],[44,12,44,13],[45,2,45,3],[45,5,45,6],[45,7,45,8],[45,10,45,11],[45,12,45,13],[46,2,46,3],[46,5,46,6],[46,7,46,8],[46,10,46,11],[46,12,46,13],[47,2,47,3],[47,5,47,6],[47,7,47,8],[47,10,47,11],[47,12,47,13],[48,2,48,3],[48,5,48,6],[48,7,48,8],[48,10,48,11],[48,12,48,13],[49,2,49,3],[49,5,49,6],[49,7,49,8],[49,10,49,11],[49,12,49,13],[50,0,50,13],[51,8,51,13],[52,0,52,2],[52,8,52,12]],"flags":["formulas_cached_only"]}
["总价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第1页 共2页"]
["序号","项目编码","项目名称",null,"计算基础","费率（%）",null,"金额（元）",null,"调整\n费率（%）","调整后\n金额（元）",null,"备注"]
["1","011707001001","安全文明施工费",null,null,""]
["1.1",null,"基本费",null,"分部分项合计+单价措施项目合计-除税工程设备费","1.500"]
["1.2",null,"增加费",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["1.3",null,"扬尘污染防治增加费",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["2","011707002001","夜间施工",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["3","011707003001","非夜间施工照明",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["4","011707004001","二次搬运",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["5","011707005001","冬雨季施工",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["6","011707006001","地上、地下设施、建筑物的临时保护设施",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["7","011707007001","已完工程及设备保护",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["8","011707008001","临时设施",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
[]
[]
[]
[{"$nulls":8},"【新点2013清单造价江苏版 V10.3.2】"]
["编制人（造价人员）：",{"$nulls":7},"复核人（造价工程师）："]
["总价措施项目清单与计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":5},"标段：",{"$nulls":4},"第2页 共2页"]
["序号","项目编码","项目名称",null,"计算基础","费率（%）",null,"金额（元）",null,"调整\n费率（%）","调整后\n金额（元）",null,"备注"]
["9","011707009001","赶工措施",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["10","011707010001","工程按质论价",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["11","011707011001","住宅分户验收",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
["12","011707012001","特殊条件下施工增加费",null,"分部分项合计+单价措施项目合计-除税工程设备费",""]
{"$rows_empty":25}
[{"$nulls":8},"【新点2013清单造价江苏版 V10.3.2】"]
["编制人（造价人员）：",{"$nulls":7},"复核人（造价工程师）："]

{"sheet":"3.3 表-12 其他项目清单与计价汇总表","index":2,"n_rows":44,"n_cols":8,"rows_kept":44,"merged":[[0,0,0,7],[1,0,1,2],[1,3,1,6],[2,2,2,3],[2,4,2,5],[2,6,2,7],[3,2,3,3],[3,4,3,5],[3,6,3,7],[4,2,4,3],[4,4,4,5],[4,6,4,7],[5,2,5,3],[5,4,5,5],[5,6,5,7],[6,2,6,3],[6,4,6,5],[6,6,6,7],[7,2,7,3],[7,4,7,5],[7,6,7,7],[8,2,8,3],[8,4,8,5],[8,6,8,7],[9,2,9,3],[9,4,9,5],[9,6,9,7],[10,2,10,3],[10,4,10,5],[10,6,10,7],[11,2,11,3],[11,4,11,5],[11,6,11,7],[12,2,12,3],[12,4,12,5],[12,6,12,7],[13,2,13,3],[13,4,13,5],[13,6,13,7],[14,2,14,3],[14,4,14,5],[14,6,14,7],[15,2,15,3],[15,4,15,5],[15,6,15,7],[16,2,16,3],[16,4,16,5],[16,6,16,7],[17,2,17,3],[17,4,17,5],[17,6,17,7],[18,2,18,3],[18,4,18,5],[18,6,18,7],[19,2,19,3],[19,4,19,5],[19,6,19,7],[20,2,20,3],[20,4,20,5],[20,6,20,7],[21,2,21,3],[21,4,21,5],[21,6,21,7],[22,2,22,3],[22,4,22,5],[22,6,22,7],[23,2,23,3],[23,4,23,5],[23,6,23,7],[24,2,24,3],[24,4,24,5],[24,6,24,7],[25,2,25,3],[25,4,25,5],[25,6,25,7],[26,2,26,3],[26,4,26,5],[26,6,26,7],[27,2,27,3],[27,4,27,5],[27,6,27,7],[28,2,28,3],[28,4,28,5],[28,6,28,7],[29,2,29,3],[29,4,29,5],[29,6,29,7],[30,2,30,3],[30,4,30,5],[30,6,30,7],[31,2,31,3],[31,4,31,5],[31,6,31,7],[32,2,32,3],[32,4,32,5],[32,6,32,7],[33,2,33,3],[33,4,33,5],[33,6,33,7],[34,2,34,3],[34,4,34,5],[34,6,34,7],[35,2,35,3],[35,4,35,5],[35,6,35,7],[36,2,36,3],[36,4,36,5],[36,6,36,7],[37,2,37,3],[37,4,37,5],[37,6,37,7],[38,2,38,3],[38,4,38,5],[38,6,38,7],[39,2,39,3],[39,4,39,5],[39,6,39,7],[40,2,40,3],[40,4,40,5],[40,6,40,7],[41,0,41,1],[41,2,41,3],[41,4,41,5],[41,6,41,7],[43,5,43,7]],"flags":["formulas_cached_only"]}
["其他项目清单与计价汇总表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",null,null,"标段：",{"$nulls":3},"第1页 共1页"]
["序号","项目名称","金额(元)",null,"结算金额(元)",null,"备注"]
["1","暂列金额",""]
["2","暂估价",""]
["2.1","材料暂估价",""]
["2.2","专业工程暂估价",""]
["3","计日工",""]
["4","总承包服务费",""]
{"$rows_empty":32}
["合  计",null,""]
[]
[{"$nulls":5},"【新点2013清单造价江苏版 V10.3.2】"]

{"sheet":"3.4 表-13 规费、税金项目计价表","index":3,"n_rows":42,"n_cols":10,"rows_kept":42,"merged":[[0,0,0,10],[1,0,1,3],[1,4,1,7],[1,8,1,10],[2,2,2,5],[2,7,2,8],[2,9,2,10],[3,2,3,5],[3,7,3,8],[3,9,3,10],[4,2,4,5],[4,7,4,8],[4,9,4,10],[5,2,5,5],[5,7,5,8],[5,9,5,10],[6,2,6,5],[6,7,6,8],[6,9,6,10],[7,2,7,5],[7,7,7,8],[7,9,7,10],[8,2,8,5],[8,7,8,8],[8,9,8,10],[9,2,9,5],[9,7,9,8],[9,9,9,10],[10,2,10,5],[10,7,10,8],[10,9,10,10],[11,2,11,5],[11,7,11,8],[11,9,11,10],[12,2,12,5],[12,7,12,8],[12,9,12,10],[13,2,13,5],[13,7,13,8],[13,9,13,10],[14,2,14,5],[14,7,14,8],[14,9,14,10],[15,2,15,5],[15,7,15,8],[15,9,15,10],[16,2,16,5],[16,7,16,8],[16,9,16,10],[17,2,17,5],[17,7,17,8],[17,9,17,10],[18,2,18,5],[18,7,18,8],[18,9,18,10],[19,2,19,5],[19,7,19,8],[19,9,19,10],[20,2,20,5],[20,7,20,8],[20,9,20,10],[21,2,21,5],[21,7,21,8],[21,9,21,10],[22,2,22,5],[22,7,22,8],[22,9,22,10],[23,2,23,5],[23,7,23,8],[23,9,23,10],[24,2,24,5],[24,7,24,8],[24,9,24,10],[25,2,25,5],[25,7,25,8],[25,9,25,10],[26,2,26,5],[26,7,26,8],[26,9,26,10],[27,2,27,5],[27,7,27,8],[27,9,27,10],[28,2,28,5],[28,7,28,8],[28,9,28,10],[29,2,29,5],[29,7,29,8],[29,9,29,10],[30,2,30,5],[30,7,30,8],[30,9,30,10],[31,2,31,5],[31,7,31,8],[31,9,31,10],[32,2,32,5],[32,7,32,8],[32,9,32,10],[33,2,33,5],[33,7,33,8],[33,9,33,10],[34,2,34,5],[34,7,34,8],[34,9,34,10],[35,2,35,5],[35,7,35,8],[35,9,35,10],[36,2,36,5],[36,7,36,8],[36,9,36,10],[38,0,38,8],[38,9,38,10],[40,5,40,10],[41,0,41,2],[41,5,41,9]],"flags":["formulas_cached_only"]}
["规费、税金项目计价表"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":3},"标段：",{"$nulls":3},"第1页 共1页"]
["序号","项目名称","计算基础",{"$nulls":3},"计算基数(元)","计算费率(％)",null,"金额(元)"]
["1","规费","工程排污费+社会保险费+住房公积金",{"$nulls":4},"100.000"]
["1.1","社会保险费","分部分项工程费+措施项目费+其他项目费-除税工程设备费",{"$nulls":4},"3.800"]
["1.2","住房公积金","分部分项工程费+措施项目费+其他项目费-除税工程设备费",{"$nulls":4},"0.670"]
["1.3","环境保护税","分部分项工程费+措施项目费+其他项目费-除税工程设备费",{"$nulls":4},"0.100"]
["2","税金","分部分项工程费+措施项目费+其他项目费+规费-除税甲供材料和甲供设备费/1.01",{"$nulls":4},"9.000"]
{"$rows_empty":30}
["合  计"]
[]
[{"$nulls":5},"【新点2013清单造价江苏版 V10.3.2】"]
["编制人（造价人员）：",{"$nulls":4},"复核人（造价工程师）："]

{"sheet":"3.5 表-21 承包人材料设备（适用于造价信息差额调整法）","index":4,"n_rows":43,"n_cols":13,"rows_kept":43,"merged":[[0,0,0,12],[1,0,1,4],[1,5,1,9],[1,10,1,12],[2,4,2,5],[2,7,2,8],[2,9,2,10],[3,4,3,5],[3,7,3,8],[3,9,3,10],[4,4,4,5],[4,7,4,8],[4,9,4,10],[5,4,5,5],[5,7,5,8],[5,9,5,10],[6,4,6,5],[6,7,6,8],[6,9,6,10],[7,4,7,5],[7,7,7,8],[7,9,7,10],[8,4,8,5],[8,7,8,8],[8,9,8,10],[9,4,9,5],[9,7,9,8],[9,9,9,10],[10,4,10,5],[10,7,10,8],[10,9,10,10],[11,4,11,5],[11,7,11,8],[11,9,11,10],[12,4,12,5],[12,7,12,8],[12,9,12,10],[13,4,13,5],[13,7,13,8],[13,9,13,10],[14,4,14,5],[14,7,14,8],[14,9,14,10],[15,4,15,5],[15,7,15,8],[15,9,15,10],[16,4,16,5],[16,7,16,8],[16,9,16,10],[17,4,17,5],[17,7,17,8],[17,9,17,10],[18,4,18,5],[18,7,18,8],[18,9,18,10],[19,4,19,5],[19,7,19,8],[19,9,19,10],[20,4,20,5],[20,7,20,8],[20,9,20,10],[21,4,21,5],[21,7,21,8],[21,9,21,10],[22,4,22,5],[22,7,22,8],[22,9,22,10],[23,4,23,5],[23,7,23,8],[23,9,23,10],[24,4,24,5],[24,7,24,8],[24,9,24,10],[25,4,25,5],[25,7,25,8],[25,9,25,10],[26,4,26,5],[26,7,26,8],[26,9,26,10],[27,4,27,5],[27,7,27,8],[27,9,27,10],[28,4,28,5],[28,7,28,8],[28,9,28,10],[29,4,29,5],[29,7,29,8],[29,9,29,10],[30,4,30,5],[30,7,30,8],[30,9,30,10],[31,4,31,5],[31,7,31,8],[31,9,31,10],[32,4,32,5],[32,7,32,8],[32,9,32,10],[33,4,33,5],[33,7,33,8],[33,9,33,10],[34,4,34,5],[34,7,34,8],[34,9,34,10],[35,4,35,5],[35,7,35,8],[35,9,35,10],[36,4,36,5],[36,7,36,8],[36,9,36,10],[37,4,37,5],[37,7,37,8],[37,9,37,10],[38,4,38,5],[38,7,38,8],[38,9,38,10],[39,4,39,5],[39,7,39,8],[39,9,39,10],[40,4,40,5],[40,7,40,8],[40,9,40,10],[41,0,41,12],[42,8,42,12]],"flags":["formulas_cached_only"]}
["承包人提供主要材料和工程设备一览表\n（适用造价信息差额调整法）"]
["工程名称：行政办公楼一层、二层卫生间改造工程",{"$nulls":4},"标段：",{"$nulls":4},"第1页 共1页"]
["序号","材料编码","名称、规格、型号","单位","数量",null,"风险系数\n(%)","基准单价\n(元)",null,"投标单价\n(元)",null,"发承包人\n确认单价\n(元)","备注"]
{"$rows_empty":39}
[{"$nulls":8},"【新点2013清单造价江苏版 V10.3.2】"]